## Timeline
Phase | Task | Status
WEEK 12-10: INITIAL PLANNING | Define conference objectives
WEEK 12-10: INITIAL PLANNING | Set preliminary budget
WEEK 12-10: INITIAL PLANNING | Form planning committee
WEEK 12-10: INITIAL PLANNING | Select date and venue
WEEK 12-10: INITIAL PLANNING | Create master timeline
WEEK 10-8: VENUE & LOGISTICS | Sign venue contract
WEEK 10-8: VENUE & LOGISTICS | Book room blocks
WEEK 10-8: VENUE & LOGISTICS | Arrange catering
WEEK 10-8: VENUE & LOGISTICS | Plan AV requirements
WEEK 10-8: VENUE & LOGISTICS | Design floor plan
WEEK 8-6: PROGRAM DEVELOPMENT | Confirm speakers
WEEK 8-6: PROGRAM DEVELOPMENT | Finalize agenda
WEEK 8-6: PROGRAM DEVELOPMENT | Create session descriptions
WEEK 8-6: PROGRAM DEVELOPMENT | Plan networking events
WEEK 8-6: PROGRAM DEVELOPMENT | Organize exhibits/sponsors
WEEK 6-4: MARKETING & REGISTRATION | Launch registration site
WEEK 6-4: MARKETING & REGISTRATION | Send save-the-dates
WEEK 6-4: MARKETING & REGISTRATION | Create marketing materials
WEEK 6-4: MARKETING & REGISTRATION | Post on social media
WEEK 6-4: MARKETING & REGISTRATION | Send press releases
WEEK 4-2: MATERIALS & PREPARATION | Print name badges
WEEK 4-2: MATERIALS & PREPARATION | Prepare welcome packets
WEEK 4-2: MATERIALS & PREPARATION | Create signage
WEEK 4-2: MATERIALS & PREPARATION | Finalize presentations
WEEK 4-2: MATERIALS & PREPARATION | Brief staff/volunteers
WEEK 2-1: FINAL PREPARATIONS | Confirm all vendors
WEEK 2-1: FINAL PREPARATIONS | Send final attendee information
WEEK 2-1: FINAL PREPARATIONS | Conduct walk-through
WEEK 2-1: FINAL PREPARATIONS | Prepare on-site materials
WEEK 2-1: FINAL PREPARATIONS | Review emergency procedures
DAY OF EVENT | Arrive early for setup
DAY OF EVENT | Brief all staff
DAY OF EVENT | Test all equipment
DAY OF EVENT | Manage registration
DAY OF EVENT | Handle issues as they arise
POST-EVENT | Send thank you notes
POST-EVENT | Compile attendee feedback
POST-EVENT | Process final payments
POST-EVENT | Create event report
POST-EVENT | Plan follow-up

## Budget Tracker
Category | Budgeted | Actual | Variance
Venue
Catering
Speakers
AV/Tech
Materials
Marketing
Staff
Other
TOTAL

## Vendor Contacts
Service | Company | Contact | Phone | Email | Notes
Venue
Catering
AV
Hotels
Transport

## Speaker Tracking
Speaker | Topic | Date/Time | AV Needs | Travel | Hotel | Status

## Registration Summary
Field | Value
Registration Open Date
Early Bird Deadline
Regular Deadline
Target Attendance

## Registration Weekly
Week | Registered | Paid | Pending | Cancelled
1
2
3
4

## Task Assignments
Task | Owner | Due Date | Status | Notes

## Risk Management
Risk | Probability | Impact | Mitigation Plan
Low attendance | Medium | High | Early bird discounts
Speaker cancellation | Low | High | Backup speakers ready
Technical issues | Medium | Medium | Test all equipment
Weather | Low | High | Indoor backup plan